## to RC1
date added | date closed | status* | —>h?** | category |  |  |  | problem | key
[9 empty] | * | —>h? = pushed to heroku version of the site?
[9 empty] | ** | twfar='that way for a reason";
ui/layout related
2012-03-29 | 2012-03-30 | changed | yes |  |  |  | 1 | TruMedical —> About TruMedical in menu
2012-03-29 | 2012-03-30 | changed | yes |  |  |  | 2 | color of footer: gray->black
2012-03-29 | 2012-03-31 | fixed | yes |  |  |  | 3 | vertical band of white to the right
2012-03-29 |  | reviewed sample w/Bill | no |  |  |  | 4 | add Tru-Medical logomark to pages; make it fade-in as well as slide down the page
2012-03-29 | [6 empty] | 5 | Insert LTL trucking and latex-free icons on product page templates
— views/products.html.erb
— views/base_products.html.erb
— views/product_sets.html.erb
— views/product_types.html.erb
2012-03-29 | [6 empty] | 6 | Fill out description fields in product tables with dots
| 2012-04-01 | [6 empty] | — views/products.html.erb
| 2012-04-01 | done | [5 empty] | — views/base_products.html.erb
| 2012-04-01 | [6 empty] | — views/product_sets.html.erb
| 2012-04-01 | [6 empty] | — view/product_types.html.erb
| 2012-04-01 | [6 empty] | — editing web_description field in products table to supply the shorter descriptions analgous to those used in the print catelog
2012-03-30 |  | twfar |  |  |  |  | 7 | Home Page > Orthopedic Products & Supplies > Splinting > Thermoplastics Need to be able to go back up this tree step by step…. Not just back to home page.
2012-03-30 |  | twfar? |  |  |  |  | 8 | Bottom Bar is not at bottom of screen on all pages, needs to be…. If page is long then you scroll to you get to the end…. If info is short the bottom bar needs to be at bottom.
2012-03-30 |  | twfar |  |  |  |  | 9 | Once you click onto a left menu item and then go to the right to select a category you should not be able to have another left side category be hovered over and snag you up.
2012-03-30 | 2012-03-31 | added | yes |  |  |  | 10 | Need Home button at top area.
2012-03-31 | 2012-03-31 | changed | yes |  |  |  | 11 | LL Category page template: increase height of product boxes to accommodate 3-line product names; in views/categories/show.html.erb — move to a .css file?
2012-03-31 | 2012-03-31 | done | yes |  |  |  |  | — Change clipping of product name in views/categories/show.html.erb from 37 to 40 characters to take advantage of the 3rd line
2012-03-31 | 2012-03-31 | done | [5 empty] | — Check for cases in which a single word is longer than a row:one: ste…; hypenated it; [ need non-hyphenated version for product title in product page template ]
2012-03-31 | 2012-03-31 | done
content-related
pictures
missing/wrong/we didn't pick up a pic that Mandy sent
2012-03-30 | 2012-03-31 | changed | yes |  |  |  | 12 | Tru-Band Pic is old. Mandy did send replacement and she will send again. referring to: Cinical Products / Resistive Exercise / Banding & Tubing/ Tru-Exercise Band (72005-000.jpg)?
2012-03-30 | 2012-03-31 | fixed | yes |  |  |  | 13 | Spell Elbow correctly in Orthopedic section
2012-03-30 | 2012-03-31 | [5 empty] | 14 | Only one pic showing up in elbow section… Why? Three reasons:
|  | fixed | yes |  |  |  |  | (1) images names in db were incorrect: 750123-900 vs. 750123-000;
|  | missing image:750124 | [5 empty] | (2) we are missing the image for 750124-000
|  | fixed | yes |  |  |  |  | (3) the latter is missing part _number and has image_url 0-000 in spreadsheet used to load database. Should be 750119-900.
2012-03-30 |  | missing image:750178 |  |  |  |  | 15 | Where is Lateral J Knee Brace pic…. Does Mandy need to send again? ( Orthodepics/Knee 750178-000.jpg ) Yes. We don't have this image.
2012-03-30 | 2012-03-31 | changed | yes |  |  |  | 16 | Under Modalities, Continuous Passive Motion pic is wrong; Mandy sent the right pic [ images/categories/all/710168-00.jpg ]
2012-03-30 | [6 empty] | 17 | Mandy will provide additional pics for Quantum fitness equipment
2012-03-30 | [6 empty] | 18 | True TX M Elliptical Pic will not work, Mandy to send replacement. Where in site?
2012-03-30 | [6 empty] | 19 | Mandy will provide Compression Unit & Sleeves Pic & I will provide content. Where in site?
2012-03-31 | [6 empty] | 20 | Need icon for LTL trucking; others?: find/create one like that used in print category
2012-03-31 | 2012-03-31 | fixed | yes |  |  |  | 21 | EpX OSFA wristband ( Rails-id 1623) 75-0105-900: products table missing tms-part no, and image file
2012-03-31 | 2012-03-31 | fixed | yes |  |  |  | 22 | Polar Heart Rate Monitors (770042 —line 2150
2012-03-31 | 2012-03-31 | fixed | yes |  |  |  | 23 | Evaluation/Pulse Wall Mount & Mobile Blood Pressure monitors 770060
2012-03-31 | 2012-03-31 | fixed | yes |  |  |  | 24 | Wound Care/ Woiund Management / Dressings: OpSite Dressing (790042)
2012-03-31 |  | missing image: 790064 |  |  |  |  | 25 | 790064-000 — missing image: Wound Care / Wound Management / Curity Strip
stretched/squished/too large
2012-03-30 | [7 empty] | All pics in Taping & Wrapping are too large
| 2012-03-31 | fixed | yes |  |  |  | 26 | — 'large' images used on product pages are squished to 72px; should be 250px high; width open as long as inside 700px.
| 2012-03-31 | fixed | yes |  |  |  | 27 | — several of the product images used on leaf-level category pages for Taping & Wrapping/Wrapping are too large.
| 2012-03-31 | fixed | yes |  |  |  |  | — — 76003 /760004 / 760007 / 760033 / 760043-47, 760035, 760055
| 2012-03-31 | fixed | yes |  |  |  | 28 | — Taping&Wrapping/Tape: Johnson&Johnson Zonas LLC image (76008) too high
| 2012-03-31 | fixed | yes |  |  |  | 29 | — ATX&Taping/First-Aid Rescue Breather LLC image (Images/Products/AllSmall/760056-000) too high
| 2012-03-31 | fixed | yes |  |  |  | 30 | — ATX&Taping/First-Aid 750054 too high to fit in 120x80
2012-03-31 | 2012-03-31 | fixed | yes |  |  |  | 31 | — ATC/Taping: subcategory image for FirstAid is stretched
2012-03-30 | 2012-03-31 | fixed | yes |  |  |  | 32 | Clnic Supplies/Education Category Pic is Stretched (images/categories/all/720311-000.jpg)
text content
2012-03-30 | [6 empty] | 33 | Compression Unit & Sleeves: Bill will provide content
categorization/consolidation
2012-03-30 |  | LLC->Product is 1:n, not m:n |  |  |  |  | 34 | Make Sombra in Dual location, add to Topical Analgesics under Clinic Supplies
2012-03-30 | 2012-03-31 | done | ys |  |  |  | 35 | Consolidate Formfit Wrist Brace in Orthopedics/Hand & Wrist 750103- (8”) & 750104- (6”) together. Put additional bullet to read Offered in both 6” and 8” models
2012-03-30 |  | LLC->Product is 1:n, not m:n |  |  |  |  | 36 | Place Sling (currently in Collars & Slings) also in Shoulder as well
2012-03-30 | 2012-03-31 | done | yes |  |  |  | 37 | Consolidate Stainless Steel Goniometers in Eval section
2012-03-30 | 2012-03-31 | done | yes |  |  |  | 38 | Take out NPWT Canister & NPWT Non-Canister from Wound Care
2012-03-31 | 2012-03-31 | done | yes |  |  |  | 39 | Gauze sponges xx0049, ..51, …52 but NOT …50
2012-03-31 | 2012-03-31 | done | yes |  |  |  | 40 | Evaluation/PulseEval/Wall Mount & Mobile Blood Pressure Monitors 770060/61?
other
functionality-related
2012-03-30 | [6 empty] | 41 | We also need to go through the process of a registration/Order Process/Checkout/UPS confirmation E-Mail/Look at My Account/How to set up an existing NetSuite Account on Web/How to set up non NetSuite customer on web. How do we promote to each group. How does these transactions Affect NetSuite and will it run smoothly.
2012-03-30 | [6 empty] | 42 | Gameplan for Promotion area and Tru Family of Products Buttons?
24 of 41. Of these, 5 not doable; another 3 waiting images; so 24 of 33 possible, =73%

## Clinics & Ordering
date added | date closed | status* | —>h?** | category |  |  |  | problem | key
[9 empty] | * | —>h? = pushed to heroku version of the site?
[9 empty] | ** | twfar='that way for a reason";
functionality-related
2012-03-30 |  |  |  |  | 41 | We also need to go through the process of a registration/Order Process/Checkout/UPS confirmation E-Mail/Look at My Account/How to set up an existing NetSuite Account on Web/How to set up non NetSuite customer on web. How do we promote to each group. How does these transactions Affect NetSuite and will it run smoothly.
|  | in; retest after moving links |  |  |  | 1 | devise-based registration subsystem on Rails side
[6 empty] | 2 | test database of two clinics with clinicians
[6 empty] | 3 | run tests to see that clinician logging in from these clinics sees the correct prices, as does someone who is not looged in
[6 empty] | 4 | test that orders are being pushed to the Netsuite back-end with clinic-specific pricing
[6 empty] | 5 | confirm that correct descriptions, UPS 8.95 shipping charges, etc. are on the Netsuite-generated shopping cart
[6 empty] | 6 | confirm that clicking the checkout-option onl such a cart does the right thing:
[7 empty] | 1 | asks for CC information ( or do we have a bill-to-clinic at the end of the month option)
[7 empty] | 2 | confirms the CC through a payment gateway, and puts a provisional charge on the card
[7 empty] | 3 | isses the correct order to warehouse to have the products on the order pulled, packed, shipped
[7 empty] | 4 | sends the customer an email confirming that the order has been shipped and giving him a tracking number
[6 empty] | 7 | In R2: add option for administrator at a clinic to manage the set of clinicians registered through her clinic through the /admin subsysgtem on the Ruby-on-Rails middle-tier
[6 empty] | 8 | [ Look at My Account? — invoke the Netsuite function ]
[ What, specifically, do you want the user to be able to see/do? ]
[ Create a separate, aggregate account, for the clinic admin? ]