## Sheet1
to implement Custom Search in TruMedical site
(test) file | date | status
|  |  | 1 | create site
|  |  |  | 1 | create tms/heroku.com in heroku account
|  |  |  | 2 | rename tm2ror tms (so that it matches name of site on heroku)
| 2011-07-14 | done |  | 3 | strip unused images out of tms so that heroku chunk won’t be too big — zip of tm2ror is currently ~ 600MB: why?
| 18MB | done |  |  | 1 | run size analysis software against tm2ror to see where the problem is: (answer: activant file was in here and in .git )
|  |  |  | 4 | create tms site in heroku
|  |  |  | 5 | set up git repo within local tms
|  |  |  | 6 | add/commit
|  |  |  | 7 | push to repo on heroku
|  |  |  | 8 | confirm that can bring up home, category, product and site#search pages from heroku
|  |  | 2 | create google site map
|  |  |  | 1 | create an XML sitemap for this site using xml-sitemap.com
|  |  |  | 2 | upload it to Google
|  |  |  | 3 | ask Google to do an immediate index of the site
|  |  | 3 | define Custom Search site in Google aiming it at tms.heroku.com
| 2011-07-14 | done |  | 1 | have Bill sign up for entry level Custom Site
| 2011-07-14 | done |  | 2 | transfer that to me as administrator
|  |  |  | 3 | confirm that I can log into it [and change name, or will it already have been changed?]
|  |  |  | 4 | try it — after figuring out what keywords will return at least some sort of search result given how little content is on the site now
|  |  | 4 | make modifications to code base: search box, and results page
|  |  |  | 1 | configure search using google
|  |  |  | 2 | insert generated code for search box in category.display.html.erb
|  |  |  | 3 | insert generated code for search results into site#search.html.erb
|  |  |  | 4 | insert route in routes.rb — not sure what routes are necessary?
|  |  |  | 5 | try it