## Sheet1
date added | date closed | status | category |  |  | problem
ui/layout related
2012-03-29 | 2012-03-30 | fixed |  |  | 1 | TruMedical —> About TruMedical in menu
2012-03-29 | 2012-03-30 | fixed |  |  | 2 | color of footer: gray->black
2012-03-29 |  |  |  |  | 3 | vertical band of white to the right
2012-03-29 |  | reviewed sample w/Bill |  |  | 4 | add Tru-Medical logomark to pages
2012-03-30 |  |  |  |  | 5 | Home Page > Orthopedic Products & Supplies > Splinting > Thermoplastics Need to be able to go back up this tree step by step…. Not just back to home page.
2012-03-30 |  |  |  |  | 6 | Bottom Bar is not at bottom of screen on all pages, needs to be…. If page is long then you scroll to you get to the end…. If info is short the bottom bar needs to be at bottom.
2012-03-30 |  |  |  |  | 7 | Once you click onto a left menu item and then go to the right to select a category you should not be able to have another left side category be hovered over and snag you up.
2012-03-30 |  |  |  |  | 8 | Need Home button at top area.
content-related
pictures
missing/wrong/we didn't pic up a pic that Mandy sent
2012-03-30 |  |  |  |  | 9 | True TX M Elliptical Pic will not work, Mandy to send replacement
2012-03-30 |  |  |  |  | 10 | Tru-Band Pic is old. Mandy did send replacement and she will send again.
2012-03-30 |  |  |  |  | 11 | Mandy will provide additional pics for Quantum fitness equipment
2012-03-30 |  |  |  |  | 12 | Spell Elbow correctly in Orthopedic section, also only one pic shoeing up in elbow section… Why?
2012-03-30 |  |  |  |  | 13 | Where is Lateral J Knee Brace pic…. Does Mandy need to send again?
2012-03-30 |  |  |  |  | 14 | Under Modalities, Continuous Passive Motion pic is wrong; Mandy sent the right pic
stretched/squished/too large
2012-03-30 |  |  |  |  | 15 | All pics in Taping & Wrapping are too large
2012-03-30 |  |  |  |  | 16 | Where is Lateral J Knee Brace pic…. Does Mandy need to send again?
2012-03-30 |  |  |  |  | 17 | Education Category Pic is Stretched
2012-03-31 |  |  |  |  | 18 | Need icons for LTL trucking, no-latex, etc; using stand-ins now
text content
2012-03-30 |  |  |  |  | 19 | Mandy will provide Compression Unit & Sleeves Pic & I will provide content
categorization/consolidation
2012-03-30 |  |  |  |  | 20 | Make Sombra in Dual location, add to Topical Analgesics under Clinic Supplies
2012-03-30 |  |  |  |  | 21 | Consolidate Formfit Wrist Brace in Orthopedics/Hand & Wrist 750103- (8”) & 750104- (6”) together. Put additional bullet to read Offered in both 6” and 8” models
2012-03-30 |  |  |  |  | 22 | Place Sling (currently in Collars & Slings) also in Shoulder as well
2012-03-30 |  |  |  |  | 23 | Consolidate Stainless Steel Goniometers in Eval section
2012-03-30 |  |  |  |  | 24 | Mandy will provide Compression Unit & Sleeves Pic & I will provide content
2012-03-30 |  |  |  |  | 25 | Take out NPWT Canister & NPWT Non-Canister from Wound Care
other
2012-03-30 |  |  |  |  | 26 | Gameplan for Promotion area and Tru Family of Products Buttons?
functionality-related
2012-03-30 |  |  |  |  | 27 | We also need to go through the process of a registration/Order Process/Checkout/UPS confirmation E-Mail/Look at My Account/How to set up an existing NetSuite Account on Web/How to set up non NetSuite customer on web. How do we promote to each group. How does these transactions Affect NetSuite and will it run smoothly.
2012-03-30 |  |  |  |  | 28 | Gameplan for Promotion area and Tru Family of Products Buttons?