## Google Search
implement Custom Search in TruMedical site
(test) file | date | status
|  |  | 1 | create site
|  |  |  | 1 | go to tm2ror; create heroku trumedical2
| 2011-07-14 | done |  | 2 | strip unused images out of tms so that heroku chunk won’t be too big — zip of tm2ror is currently ~ 600MB: why?
| 18MB | done |  |  | 1 | run size analysis software against tm2ror to see where the problem is: (answer: activant file was in here and in .git )
| 2011-07-14 | done |  | 3 | create trumedical2 app in heroku
| 2011-07-14 | done |  | 4 | set up git repo within local tm2ror that links to trumedical2 on heroku
| 2011-07-14 | done |  | 5 | add/commit
| 2011-07-14 | done |  | 6 | push to repo on heroku
| 2011-07-14 | done |  | 7 | confirm that can bring up home, category, product and site#search pages from heroku
|  |  | 2 | create google site map
| 2011-07-14 | done |  | 1 | create XML sitemaps for trumedical2.heroku.com and trumedical.heroku.com (because the first one doesn't have any links)
| 2011-07-14 | done |  | 2 | upload sites maps to /public directories within trumedical.heroku and trumedical2.heroku
| 2011-07-14 | done |  | 3 | go through Google validation that I am the owner of these sites: insert html file provided by google in /public or <meta> tag in index page ( by inserting it into layout files: application.html.erb or, in the case of trumedical, the separate layout file for the home page, home.html.erb
|  |  |  | 4 | submit sitemaps for the two sites to Google; for trumedical2.heroku.com, submit both sites maps (after uploading both to trumedical2.heroku.com's public directory
| 2011-07-15 | done |  |  | — | for trumedical (design #1)
| 2011-07-15 | done |  |  | — | for trumedical2 (design #2: mavic inspired)
|  |  | 3 | define Custom Search site in Google telling it to search both trumedical2.heroku and the original site trumedical.heroku, since there are entries only in the site map for trumedical.heroku and we want to experiment with formatting the search results in trumedical2.heroku.com
| 2011-07-14 | done |  | 1 | have Bill sign up for entry level Custom Site
| 2011-07-14 | done |  | 2 | transfer that to me as administrator
|  | done |  | 3 | confirm that I can log into it [and change name, or will it already have been changed?]
|  | fixed |  | 4 | try it — after figuring out what keywords will return at least some sort of search result given how little content is on the site now
|  |  | (**) | Google control panel for cse shows extra sites maps (one for vms365) associated with the search engine for TruMedical. How did that happen? And how do I remove it?
|  |  | 4 | make modifications to code base: search box, and results page
| 2011-07-15 | done |  | 1 | configure search using Google command interface (http://google.com/sitesearch/ using Google account thomas.atwood07@gmail.co) — this rather than XML configuration file
[5 empty] | — | unclear what query parameter option was: not discussed in the documentation; defaults to /?q=
| 2011-07-15 | done |  | 2 | insert generated code for search box in category.display.html.erb
| 2011-07-15 | done |  | 3 | insert generated code for search results into site#search.html.erb
| 2011-07-15 | none |  | 4 | insert route in routes.rb — not sure what routes are necessary?
| 2011-07-15 | done |  | 5 | try it
| 2011-07-15 | fixed |  |  | — | search box is screwing up the layout of category#display.html
| 2011-07-15 | done |  |  |  | — | try embedding it in menu partial included in category#display
That keeps it within menu div, and avoids smashing layout, but style needs work
| 2011-07-15 | fixed |  |  | — | search results are not appearing on site#search — although it is transferring to that page
| 2011-07-15 | done |  |  |  | — | OK; it was xfering to page on heroku not local host
|  |  |  | 6 | read documentation on RESTful API to Search that returns results as JSON; read existing mavic code to see if that is how it is embedding Google search
|  |  |  | 7 | recover formatting of search results
|  |  |  | 8 | recover dynamic appearance of search box in menu; and formatting of box/go

## FMP SOAP
Build/test code to use FMP's implementation of the AAIA IPO v2 SOAP/WSDL API to (i) check inventory for an item about to order; (2) place an order
(test) file | date | status
|  |  | 1 | Background
|  |  |  | 1 | read into SOAP — follow links on Savon site
|  |  |  | 2 | read WSDL — follow links on Savon site
| 2011-07-15 | done |  | 3 | install SOAP_UI 4.0
— do a couple of their demos
|  |  | 2 | Review writing/running Ruby applications: erb, debugger
erb
debugger
installing gems/plugins — works with plain Ruby? or only with Rails?
|  |  | 3 | SOAP library for Ruby/Rails: Savon
| 2011-07-15 | done |  |  | install in Rails app fmp using Builder
read through documentation on the site
install it as a library/plugin that a standalone Ruby program can access
|  |  | 4 | Demo/test application(s)
|  |  |  | 1 | those in DIX book, pg 177ff
[5 empty] | — | with WSDL
[5 empty] | — | without WSDL
|  |  |  | 2 | another public SOAP API — one where I don't have code to copy
|  |  | 5 | AiAA IPO V2 API
|  |  |  | 1 | read any doc on the AAIA site
|  |  |  | 2 | Use SOAP-UI to read the WSDL and understand the operations
|  |  | 6 | FMP's implementation
|  |  |  | 1 | find Chucks email with URI of the endpoint
|  |  |  | 2 | attach to the endpoint using SOAP-UI
|  |  |  | 3 | build Ruby program to attach to it Savon library
[5 empty] | — | attempt to execute the get-inventory opeation
[5 empty] | — | attempt to execute the place-order operation
|  |  |  | 4 | do the same from within a Rails action
|  |  | 7 | AAO use of the FMP API
|  |  |  | 1 | build a stand-alone Checkout operation that verifies stock and submits order
[5 empty] | — | create a rudimentary Shopping-Cart with Checkout
[5 empty] | — | create a mock that places a set of products in the cart (all FMP products)
[5 empty] | — | at Checkout,
[6 empty] | — | check that they are still in stock
[6 empty] | — | submit order containig all (and only) those that are in stock
[ pricing, tax, shipping info? ]
[6 empty] | — | write orders submitted to database; add tracking information
[6 empty] | — | write an action that lets a user check on the status of his order [ and its scheduled ship/arrival dates? ]