## Sheet1
point release
Release 1 | [5 empty] | man days | hours | cost | bid
[8 empty] | 48 | 60
| 1 | Patient Release; Beta for Clinics/Clinicians |  |  |  | 60 | 480 | 23040 | 6500
| 1.1 | Fixes to 1.0 ( no new features: fixes only)
|  | 1 | content fixes: any of the following: |  |  | 0.5 | 4 | 192 | no charge
|  |  | — | missing products on the site
|  |  | — | missing images — for products or categories
|  |  | — | wrong image for a product or category
|  |  | — | products showing up in the wrong categories
|  |  | — | descriptions wrong
|  | 2 | set up Test and Production apps/stacks on heroku |  |  | 0.5 | 4 | 192 | no charge
|  | 3 | attach up-time monitor |  |  | 0.25 | 2 | 96 | no charge
|  | 4 | build full XML site map, and have Google CSE reindex the site |  |  | 0.25 | 2 | 96 | no charge
|  | 5 | review/revise clinic administrator / clinician registration |  |  | 0.75 | 6 | 288 | no charge
|  | 6 | modify code to enforce restriction on clinician-only products |  |  | 0.5 | 4 | 192 | no charge
Release 2: focus on Revenue Generation through the site | [7 empty] | 1056 | no charge
| 2 | broader product line, multi-competitor search
|  | 1 | broader product line
|  |  | 1 | product data/descripitons
|  |  |  | 1 | put products up on test/review site | 0.5 | 4 | 192
|  |  |  | 2 | merge with release 1 product set (reordering?) | 0.5 | 4 | 192
|  |  |  | 3 | rebuild database | 0.5 | 4 | 192
|  |  |  | 4 | push database to Heroku; use Taps to map to Postgres | 0.5 | 4 | 192
|  |  | 2 | images
|  |  |  | 1 | resize to create thumbnails and product page image | 0.5 | 4 | 192
|  |  |  | 2 | track which we have, which we're missing | 0.5 | 4 | 192
|  |  |  | 3 | upload to heroku/Amazon site | 0.5 | 4 | 192
|  |  | 3 | walk category tree in live site to confirm images present |  | 0.5 | 4 | 192
|  |  | 4 | fix any missing images / wrong images / bad descriptions, etc |  | 0.5 | 4 | 192
1728
|  | 2 | expand search-by-competitor's part# to more than Sammons |  |  | 1 | 8 | 384
[5 empty] | subtotal, release 2.0 |  |  | 2112 | 2640
| 2.1 | Clinic-Focused Functionality—#1
|  | 1 | Match Patterson purchase approval system
|  |  | 1 | in views/clinic/edit: form allowing clinic admin to specify limits |  | 0.5 | 4 | 192
|  |  | 2 | move shopping cart to middle-tier (RoR), so can: |  | 2 | 16 | 768
|  |  | 3 | accumulate sales on a per-client basis, and stop if over limit |  | 1 | 8 | 384
|  |  | 4 | log to DB and notify Clinic Admin |  | 0.5 | 4 | 192
|  |  | 5 | let Clinic Admin retrieve them when she logs in |  | 0.5 | 4 | 192
|  |  | 6 | forms to resolve them |  | 1 | 8 | 384
|  | 2 | Special discounts for specific products for individual clinics |  |  | 2 | 16 | 768
[5 empty] | subtotal, release 2.1 |  | 60 | 2880 | 3600
| 2.2 | Performance: reduce download time (*)
|  | 1 | establish baseline numbers |  |  | 0.5 | 4 | 192
|  | 2 | consolidate and compress js and css |  |  | 0.5 | 4 | 192
|  | 3 | cache left-nav to reduce SQL calls |  |  | 0.5 | 4 | 192
|  | 4 | images to separate image server ( Amazon S3)
|  |  | — | Amazon S3 |  | 0.5 | 4 | 192
|  |  | — | [ Amazon Cloudfront] |  | 1 | 8 | 384
|  | 5 | re-evaluate |  |  | 0.5 | 4 | 192
[5 empty] | subtotal, release 2.2 |  |  | 1152 | 1440
| 2.3 | Sexier UI: for products
|  |  | 1 | zoom on product images for at least the subset that we have large images for |  | 0.5 | 4 | 192
|  |  |  | (note:implies, images => Amazon S3; set expires headers ) | implies, images => Amazon S3; set expires headers | 0.5 | 4 | 192
|  |  | 2 | more engaging company panel on home page |  | 0.5 | 4 | 192
[5 empty] | subtotal, release 2.3 |  |  | 576
|  |  | Total, Release 2 (all four point releases) |  |  |  |  | 6720 | 8400
Release 3: Simplify web-site administration
( focus on reducing cost/hassle. rather than on increasing revenue)
| 3.1 | Rails-side Admin Center for managing products/categories
|  | 1 | product add/update/delete |  |  | 0.5 | 4 | 192
|  | 2 | category add/move in tree |  |  | 0.5 | 4 | 192
|  | 3 | push product/category updates to NS |  |  | 2 | 16 | 768
|  | 4 | view/edit clinic properties |  |  | 0.5 | 4 | 192
|  | 5 | push to Netsuite |  |  | 1 | 8 | 384
|  | [6] | synch Netsuite product changes -> Rails |  |  | 2 | 16 | 768
[8 empty] | 2496 | 3120
| 3.2 | Add support for managing product images[/video] serving from CDN
|  | 1 | import/resize |  |  | 0.5 | 4 | 192
|  | 2 | push to local file, and from there to heroku slug |  |  | 0.5 | 4 | 192
|  | 3 | push to Amazon S3 |  |  | 0.5 | 4 | 192
|  | 4 | [ push to Amazon Cloudfront] |  |  | 0.5 | 4 | 192
|  | 5 | Video to video CDN, eg., Brightcove/Akamai |  |  | 2 | 16 | 768
[8 empty] | 1536 | 1920
| 3.3 | Analytics
|  | 1 | generate/display Google traffic analytics |  |  | 1 | 8 | 384
|  | 2 | jQuery to retrieve Facebook analytics and plot them |  |  | 2 | 16 | 768
|  | 3 | generate/display page path/abandonment analytics |  |  | 1 | 8 | 384
[8 empty] | 1536 | 1920
|  |  | Total, Release-3 |  |  |  | 116 | 5568 | 6960
Release 4: Dealers, Reps, Affiliates, Clinic Groups
( expand site to serve broader set of types of users )
| 4 | Dealer and Rep support
|  | 1 | Dealers: subtype of User; STI implementation |  |  | 0.5 | 4 | 192
|  | 2 | Reps: subtype of User; STI implementation; can order catelogs |  |  | 0.5 | 4 | 192
[8 empty] | 384 | 480
| 4.1 | Clinic-Focused Functionality — #2
|  | 1 | Add clinic groups
|  |  | 1 | price schedule across all clinics in the group |  | 0.5 | 4 | 192
|  |  | 2 | purchase approval lilmits on individual clinic adminstrators also |  | 0.5 | 4 | 192
|  |  | 3 | aggregate purchase reporting for clinics within group |  | 2 | 16 | 768
|  | 2 | A visual toy that your rep can show clinic administrator:
|  |  | 1 | plotting all clinics in group on a map |  | 0.5 | 4 | 192
|  |  | 2 | quick clinic-on summaries of purchase Y-to-D, Month-to-Date |  | 0.5 | 4 | 192
|  |  | 3 | Google earth-based spiral down to the clinic front door from space |  | 0.5 | 4 | 192
[8 empty] | 1728 | 2160
| 4.2 | Affiliates
|  | 1 | Templates for building mini-sites |  |  | 5 | 40 | 1920
|  | 2 | Changes to pricing/billling to credit them for sales coming |  |  | 1 | 8 | 384
in through their sites
|  | 3 | Testing |  |  | 2 | 16 | 768
[8 empty] | 3072 | 3840
|  |  | Total Release 4 ( three point releases ) |  |  |  |  | 5184 | 6480
Note on E8: 2 cervical under pillows and cushions and under clinic supplies, product shown is one for positioning,in a category called pivotal …; same as bolster and web; that should not be under clinic supplies at all.
Note on F47: Want to use Rails 3.2. Depends on prior port of netsuite_client to Ruby 1.9.3.