## Sheet1
to implement Custom Search in TruMedical site
(test) file | date | status
|  |  | 1 | create site
|  |  |  | 1 | go to tm2ror; create heroku trumedical2
| 2011-07-14 | done |  | 2 | strip unused images out of tms so that heroku chunk won’t be too big — zip of tm2ror is currently ~ 600MB: why?
| 18MB | done |  |  | 1 | run size analysis software against tm2ror to see where the problem is: (answer: activant file was in here and in .git )
|  | done |  | 3 | create trumedical2 app in heroku
|  | done |  | 4 | set up git repo within local tm2ror that links to trumedical2 on heroku
|  | done |  | 5 | add/commit
|  | done |  | 6 | push to repo on heroku
|  | done |  | 7 | confirm that can bring up home, category, product and site#search pages from heroku
|  |  | 2 | create google site map
|  | done |  | 1 | create an XML sitemap for this site using xml-sitemap.com
|  |  |  | 2 | upload sites maps to /public directories within trumedical.heroku and trumedical2.heroku
|  |  |  | 3 | ask Google to do an immediate index of the site
|  |  | 3 | define Custom Search site in Google telling it to search both trumedical2.heroku and the original site trumedical.heroku, since there are entries only in the site map for trumedical.heroku and we want to experiment with formatting the search results in trumedical2.heroku.com
| 2011-07-14 | done |  | 1 | have Bill sign up for entry level Custom Site
| 2011-07-14 | done |  | 2 | transfer that to me as administrator
|  | done |  | 3 | confirm that I can log into it [and change name, or will it already have been changed?]
|  |  |  | 4 | try it — after figuring out what keywords will return at least some sort of search result given how little content is on the site now
|  |  | 4 | make modifications to code base: search box, and results page
|  |  |  | 1 | configure search using Google command interface (or wizard) — this rather than XML configuration file
|  |  |  | 2 | insert generated code for search box in category.display.html.erb
|  |  |  | 3 | insert generated code for search results into site#search.html.erb
|  |  |  | 4 | insert route in routes.rb — not sure what routes are necessary?
|  |  |  | 5 | try it