## 0410-0413
date added | date closed | status* | —>h? | category |  |  | problem |  | key
[9 empty] | * | —>h? = pushed to heroku version of the site?
[9 empty] | ** | twfar='that way for a reason";
new since 04/10
UI/Layout related:
2012-04-12 | 2012-04-13 | done | yes |  |  | 1 | get rid of gray by going back to footer relative rather than fixed; retain code in directory tm3rorFF (for 'Fixed Footer') so can work on it later
2012-04-12 | 2012-04-13 | done:OK | yes |  |  | 2 | check it on iPhone also
Content-related
2012-04-10 | 2012-04-11 | done | yes |  |  | 1 | new image for pulls: category and individual product within that category
2012-04-10 | [5 empty] | 2 | Need correct Facebook link for application.html.erb
2012-04-10 | 2012-04-12 | done | yes |  |  | 3 | get in new products for iontopohoresis (6): 'products' table tuples, images, descriptions, pricing
[7 empty] | — | 710003-001 and 710003-000 violate the convention that we can strip the xxx ending off of image filenames and replace it with 000. I have dropped it; does it break other product pages in the site?
2012-04-10 | 2012-04-12 | done | no |  |  | 4 | get in new products for category 22:'products' table tuples, images, descriptions, pricing
2012-04-10 | 2012-04-13 | done | no |  |  | 5 | do the leaf-category swap in Bill's email of April 10th: ('Website comments): move Lifeline Fitness Cables from Resistive Exercise (#33) to Band & Tubing (#34)
2012-03-30 | 2012-04-13 | done | no |  |  | 6 | insert the two items that occur in two categories; Bill's email of March 30th: UI Issues I have noticed. Items 1 and 8: Sombra —> Clinic Supplies/Topical Analgesics; Sling (currently in Collars & Slings) ->Shoulder as well (so the category is not empty)
720296-xxx: actually, just recategorize from 30 to 42 (analygsics); retitle massage products'/lotions and gels' as 'massage lotions' as in print catalog
750164-000/xxx Slings; now in category 73 ; also to category 77 base_product 1737; now duplicated at 1742-46
[6 empty] | 7 | Lymphodema/Pumps: waiting compression and compression sleeves data from Bill; there were some images for these among those Mandy sent last -- but without tms part nos. Bill's email of April 9th
2012-04-13 | 2012-04-13 | done |  |  |  |  | — | eliminate it from the category tree for now
2012-04-13 | 2012-04-13 | done | no |  |  | 8 | eliminate intermediate categories in Lymthodema and Wound Care
2012-03-30 | 2012-04-13 | fixed | no |  |  | 9 | missing products in Wound Care/Scar Management?
2012-04-13 | 2012-04-13 | done | no |  |  | 10 | use digital TENS as category for Modalities/… Personal Electrotheraphy
2012-04-13 | 2012-04-13 | done | no |  |  | 11 | change text on placeholder image for missing category images from 'missing image' to 'no image'
| 2012-04-13 |  |  |  |  | 12 | go through entire site, reviewing thumbnails and large images
[7 empty] | — | Note: change in product.html.erb to use full image_filename rather than stripping it to 6 characters and pospending '-000' will cause some breakag; will have to rename some files in allLlarge and perhaps all_small to have -001, … endings
exanples of this 720331-001