## to RC1
date added | date closed | status* | —>h?** | category |  |  |  | problem |  | key
[10 empty] | * | —>h? = pushed to heroku version of the site?
[10 empty] | ** | twfar='that way for a reason";
ui/layout related
2012-03-29 | 2012-03-30 | changed | yes |  |  |  | 1 | TruMedical —> About TruMedical in menu
2012-03-29 | 2012-03-30 | changed | yes |  |  |  | 2 | color of footer: gray->black
2012-03-29 | 2012-03-31 | fixed | yes |  |  |  | 3 | vertical band of white to the right
2012-03-29 | 2012-04-01 | done | yes |  |  |  | 4 | add Tru-Medical logomark to pages
| 2012-04-01 | done | yes |  |  |  |  | — make logomark a link to home page; [ remove 'Home' link from header: redundant ]
2012-03-29 | 2012-04-01 | done | yes |  |  |  | 5 | Insert LTL trucking and latex-free icons on product page templates
| 2012-04-01 | done | yes |  |  |  |  | — views/products/show.html.erb
| 2012-04-01 | done | yes |  |  |  |  | — views/base_products/show.html.erb
| 2012-04-01 | done | yes |  |  |  |  | — views/product_sets/show.html.erb
| 2012-04-01 | code in | yes |  |  |  |  | — views/product_types/show.html.erb
| 2012-04-01 | unneeded | yes |  |  |  |  | — views/product_types/_accessories.html.erb
| 2012-04-01 | done | yes |  |  |  |  | — insert tooltips to explain what the icons mean
2012-03-29 | [6 empty] | 6 | Fill out description fields in product tables with dots
| 2012-04-01 | done | yes |  |  |  |  | — views/base_products/show.html.erb
| 2012-04-01 | done | yes |  |  |  |  | — views/product_sets/show.html.erb
| 2012-04-01 | done | yes |  |  |  |  | — view/product_types/show.html.erb
| 2012-04-01 | done | yes |  |  |  |  | — view/product_types/_accessories.html.erb
| 2012-04-08 | done | [5 empty] | — editing web_description field in products table to supply the shorter descriptions analgous to those used in the print catelog
— e.g., category 68 (Fitness/Universal: Quantum line components): strip web_description to just the color
2012-03-30 | 2012-04-04 | done | yes |  |  |  | 7 | Home Page > Orthopedic Products & Supplies > Splinting > Thermoplastics Need to be able to go back up this tree step by step…. Not just back to home page.
2012-03-30 | 2012-04-04 | done | in tm4ror |  |  |  | 8 | Bottom Bar is not at bottom of screen on all pages, needs to be…. If page is long then you scroll to you get to the end…. If info is short the bottom bar needs to be at bottom.
2012-03-30 | 2012-04-03 | done | yes |  |  |  | 9 | Make overlays that pop up when user hovers over items in left menu, close when user mouses off of them, allowing but not forcing them to use the close button in the upper right
2012-03-30 | 2012-04-03 | done: hoverIntent | in tm4ror |  |  |  | 10 | Once you click onto a left menu item and then go to the right to select a category you should not be able to have another left side category be hovered over and snag you up.
2012-03-30 | 2012-03-31 | added | yes |  |  |  | 11 | Need Home button at top area.
2012-03-31 | 2012-03-31 | changed | yes |  |  |  | 12 | LL Category page template: increase height of product boxes to accommodate 3-line product names; in views/categories/show.html.erb — move to a .css file?
2012-03-31 | 2012-03-31 | done | yes |  |  |  |  | — Change clipping of product name in views/categories/show.html.erb from 37 to 40 characters to take advantage of the 3rd line
2012-03-31 | 2012-03-31 | done | [5 empty] | — Check for cases in which a single word is longer than a row:one: ste…; hypenated it; [ need non-hyphenated version for product title in product page template ]
2012-03-31 | 2012-04-01 | done | yes |  |  |  | 13 | Remove extraneous 'close icon' that is appearing to the far right in category pages
content-related
pictures
missing/wrong/we didn't pick up a pic that Mandy sent
2012-03-30 | 2012-03-31 | changed | yes |  |  |  | 14 | Tru-Band Pic is old. Mandy did send replacement and she will send again. referring to: Cinical Products / Resistive Exercise / Banding & Tubing/ Tru-Exercise Band (72005-000.jpg)?
2012-03-30 | 2012-03-31 | fixed | yes |  |  |  | 15 | Spell Elbow correctly in Orthopedic section
2012-03-30 | 2012-03-31 | [5 empty] | 16 | Only one pic showing up in elbow section… Why? Three reasons:
| 2012-03-31 | fixed | yes |  |  |  |  | (1) images names in db were incorrect: 750123-900 vs. 750123-000;
| 2012-04-01 | fixed | yes |  |  |  |  | (2) we are missing the image for 750124-000: Mandy supplied a new one 4/1
| 2012-03-31 | fixed | yes |  |  |  |  | (3) the latter is missing part _number and has image_url 0-000 in spreadsheet used to load database. Should be 750119-900.
2012-03-30 |  | fixed | yes |  |  |  | 17 | Where is Lateral J Knee Brace pic…. Does Mandy need to send again? ( Orthodepics/Knee 750178-000.jpg ) Yes. We don't have this image.
2012-03-30 | 2012-03-31 | changed | yes |  |  |  | 18 | Under Modalities, Continuous Passive Motion pic is wrong; Mandy sent the right pic [ images/categories/all/710168-00.jpg ]
2012-03-30 | 2012-04-03 | done | yes |  |  |  | 19 | Mandy will provide additional pics for Quantum fitness equipment — page 50-51 of the printed Catelog'
2012-04-01 | 2012-04-03 | done modulo 3 missing images | [5 empty] | — got 20 images;pulled 3 missing images from the web: 740046-000 or 740047-000,740059-000,740062-000.
— the item 740117 is used to specify 'frame color' for any of these equipment pieces
2012-03-30 | 2012-04-03 | done |  |  |  |  | 20 | True TX M Elliptical Pic will not work, Mandy to send replacement. Got replacement from the web.
2012-03-30 | [6 empty] | 21 | Mandy will provide Compression Unit & Sleeves Pic & I will provide content. Where in site? Lymphedema/Compression/Garmets: 18 images
2012-03-31 | 2012-04-01 | MP-> | yes |  |  |  | 22 | Need icon for LTL trucking, assembly required; others?: find/create one like that used in print category
2012-03-31 | 2012-03-31 | fixed | yes |  |  |  | 23 | EpX OSFA wristband ( Rails-id 1623) 75-0105-900: products table missing tms-part no, and image file
2012-03-31 | 2012-03-31 | fixed | yes |  |  |  | 24 | Polar Heart Rate Monitors (770042 —line 2150
2012-03-31 | 2012-03-31 | fixed | yes |  |  |  | 25 | Evaluation/Pulse Wall Mount & Mobile Blood Pressure monitors 770060
2012-03-31 | 2012-03-31 | fixed | yes |  |  |  | 26 | Wound Care/ Woiund Management / Dressings: OpSite Dressing (790042)
2012-03-31 | 2012-04-01 | fixed | yes |  |  |  | 27 | 790064-000 — missing image: Wound Care / Wound Management / Dressings — Curity Strip
2012-04-05 | 2012-04-06 | done |  |  |  |  | 28 | Do a systematic, thorough review of all images on the site down through leaf-level categories;
2012-04-05 | [6 empty] | 29 | Fix any/all problems this surfaces
| 2012-04-06 | done | yes |  |  |  |  | — fixed 21 of 34 problems that surfaced
— get images for 4 products that we are missing from Mandy or from the web
— do not show categories in the web site (9) that the database does not currently contain products fo
stretched/squished/too large
2012-03-30 | [7 empty] | All pics in Taping & Wrapping are too large
| 2012-03-31 | fixed | yes |  |  |  | 30 | — 'large' images used on product pages are squished to 72px; should be 250px high; width open as long as inside 700px.
| 2012-03-31 | fixed | yes |  |  |  | 31 | — several of the product images used on leaf-level category pages for Taping & Wrapping/Wrapping are too large.
| 2012-03-31 | fixed | yes |  |  |  |  | — — 76003 /760004 / 760007 / 760033 / 760043-47, 760035, 760055
| 2012-03-31 | fixed | yes |  |  |  | 32 | — Taping&Wrapping/Tape: Johnson&Johnson Zonas LLC image (76008) too high
| 2012-03-31 | fixed | yes |  |  |  | 33 | — ATX&Taping/First-Aid Rescue Breather LLC image (Images/Products/AllSmall/760056-000) too high
| 2012-03-31 | fixed | yes |  |  |  | 34 | — ATX&Taping/First-Aid 750054 too high to fit in 120x80
2012-03-31 | 2012-03-31 | fixed | yes |  |  |  | 35 | — ATC/Taping: subcategory image for FirstAid is stretched
2012-03-30 | 2012-03-31 | fixed | yes |  |  |  | 36 | Clnic Supplies/Education Category Pic is Stretched (images/categories/all/720311-000.jpg)
text content
2012-03-30 | [6 empty] | 37 | Compression Unit & Sleeves: Bill will provide content
categorization/consolidation
2012-03-30 |  | LLC->Product is 1:n, not m:n |  |  |  |  | 38 | Make Sombra in Dual location, add to Topical Analgesics under Clinic Supplies
2012-03-30 | 2012-03-31 | done | ys |  |  |  | 39 | Consolidate Formfit Wrist Brace in Orthopedics/Hand & Wrist 750103- (8”) & 750104- (6”) together. Put additional bullet to read Offered in both 6” and 8” models
2012-03-30 |  | LLC->Product is 1:n, not m:n |  |  |  |  | 40 | Place Sling (currently in Collars & Slings) also in Shoulder as well
2012-03-30 | 2012-03-31 | done | yes |  |  |  | 41 | Consolidate Stainless Steel Goniometers in Eval section
2012-03-30 | 2012-03-31 | done | yes |  |  |  | 42 | Take out NPWT Canister & NPWT Non-Canister from Wound Care
2012-03-31 | 2012-03-31 | done | yes |  |  |  | 43 | Gauze sponges xx0049, ..51, …52 but NOT …50
2012-03-31 | 2012-03-31 | done | yes |  |  |  | 44 | Evaluation/PulseEval/Wall Mount & Mobile Blood Pressure Monitors 770060/61?
functionality-related
2012-03-30 | [6 empty] | 45 | We also need to go through the process of a registration/Order Process/Checkout/UPS confirmation E-Mail/Look at My Account/How to set up an existing NetSuite Account on Web/How to set up non NetSuite customer on web. How do we promote to each group. How does these transactions Affect NetSuite and will it run smoothly.
2012-03-30 |  | —> R1.1 |  |  |  |  | 46 | Game plan for Promotion area and Tru Family of Products Buttons?
performance-related
2012-04-03 | 2012-04-03 | done | yes |  |  |  | 47 | Prempt 'flash of unstyled content' from loading images for menu overlays and then hiding then, by setting their initial display property to none in css, not in jQuery handler invoked on document ready
2012-04-03 | 2012-04-03 | done | yes |  |  |  | 48 | Preempt replayout of product, base_product, product_set and product_type pages once product image comes in, pushing down the rest, by preallocating image space at 250px of vertical space.
2012-04-03 | [6 empty] | 49 | Let Google take the rap when page load gets hung up waiting for Google-CSE-javascript to load: change 'loading' to 'loading Google Search'
new since 04/10
UI/Layout related:
2012-04-12 | 2012-04-13 | done |  |  |  |  | 1 | get rid of gray by going back to footer relative rather than fixed; retain code in directory tm3rorFF (for 'Fixed Footer') so can work on it later
2012-04-12 | 2012-04-13 | done:OK |  |  |  |  | 2 | check it on iPhone also
Content-related
2012-04-10 | 2012-04-11 | done |  |  |  |  | 1 | new image for pulls: category and individual product within that category
2012-04-10 | [6 empty] | 2 | Need correct Facebook link for application.html.erb
2012-04-10 | 2012-04-12 | done |  |  |  |  | 3 | get in new products for iontopohoresis (6): 'products' table tuples, images, descriptions, pricing
[8 empty] | — | 710003-001 and 710003-000 violate the convention that we can strip the xxx ending off of image filenames and replace it with 000. I have dropped it; does it break other product pages in the site?
2012-04-10 | 2012-04-12 | done |  |  |  |  | 4 | get in new products for category 22:'products' table tuples, images, descriptions, pricing
2012-04-10 | 2012-04-13 | done |  |  |  |  | 5 | do the leaf-category swap in Bill's email of April 10th: ('Website comments): move Lifeline Fitness Cables from Resistive Exercise (#33) to Band & Tubing (#34)
2012-03-30 | 2012-04-13 | done |  |  |  |  | 6 | insert the two items that occur in two categories; Bill's email of March 30th: UI Issues I have noticed. Items 1 and 8: Sombra —> Clinic Supplies/Topical Analgesics; Sling (currently in Collars & Slings) ->Shoulder as well (so the category is not empty)
720296-xxx: actually, just recategorize from 30 to 42 (analygsics); retitle massage products'/lotions and gels' as 'massage lotions' as in print catalog
750164-000/xxx Slings; now in category 73 ; also to category 77 base_product 1737; now duplicated at 1742-46
[7 empty] | 7 | waiting compression and compression sleeves data from Bill; there were some images for these among those Mandy sent last -- but without tms part nos. Bill's email of April 9th
2012-04-13 | 2012-04-13 | done |  |  |  |  | 8 | eliminate intermediate categories in Lymthodema and Wound Care
2012-03-30 | 2012-04-13 | fixed |  |  |  |  | 9 | missing products in Wound Care/Scar Management?
2012-04-13 | 2012-04-13 | done |  |  |  |  | 10 | use digital TENS as category for Modalities/… Personal Electrotheraphy
2012-04-13 | 2012-04-13 | done |  |  |  |  | 11 | change text on placeholder image for missing category images from 'missing image' to 'no image'
| 2012-04-13 | [5 empty] | 12 | go through entire site, reviewing thumbnails and large images
[8 empty] | — | Note: change in product.html.erb to use full image_filename rather than stripping it to 6 characters and pospending '-000' will cause some breakag; will have to rename some files in allLlarge and perhaps all_small to have -001, … endings
exanples of this 720331-001
Registration/Cart/Checkout/MyAccount / Clinilc admin related
2012-04-12 | 2012-04-12 | done |  |  |  |  | 1 | fix price display if current_user.clinician — 'clinician' link only available if logged in, prefix with if curent_user …
2012-04-12 | [6 empty] | 2 | Rails-level User/registration:
2012-04-12 | [7 empty] | 1 | final form of clinician create/edit forms: trumedical-clinic-customer-no; drop price_schedule, and clinicid
2012-04-12 | [7 empty] | 2 | Where does this form submission get handled? I need to intercept it and translate clinic-customer-no into rails id for foreign key: clinic id
2012-04-12 | [7 empty] | 3 | clinician OR consumer
2012-04-12 | [7 empty] | — | error handiing: if check clinician, but clinic#/ clinic-name don't match anything in the system?
2012-04-12 | [7 empty] | — | error handling: option to delete registration: currently going to non-existant list action; remove it entirely for now, so user can't go somewhere that generates an error?
2012-04-12 | [7 empty] | — | error handllng: confirm that clinic has a price-schedule; otherwise code to show producdts will fail?
2012-04-12 | 2012-04-13 | [5 empty] | 3 | Review Netsuite checkout/shipping options, e.g., setup that is now causing More: free shipped, delivered by Allen
| 2012-04-13 | found | [5 empty] | 1 | set up option that is now causing the cart to say: free shipping, delivered by Allen
| 2012-04-13 | done | [5 empty] | 2 | Continue Shopping' button should go back to Rails site
2012-04-12 | 2012-04-13 | in; now mask it |  |  |  |  | 4 | Clinic setup: Add a link to Netsuite my-account called 'administration' into the header if user is a clinic owner/administrator. What will/should this allow him to do?
2012-04-12 | 2012-04-13 | done |  |  |  |  | 5 | Can we skin what comes back when the owner/admin clicks this link?
2012-04-13 | [6 empty] | 6 | Handle clinician-only products: same drill: if user_logged_in? and current_user.clinician == true, then let him/her see clinician-only products, otherwise not

## Clinics & Ordering
date added | date closed | status* | —>h?** | category |  |  |  | problem | key
[9 empty] | * | —>h? = pushed to heroku version of the site?
[9 empty] | ** | twfar='that way for a reason";
functionality-related
2012-03-30 |  |  |  |  | 41 | We also need to go through the process of a registration/Order Process/Checkout/UPS confirmation E-Mail/Look at My Account/How to set up an existing NetSuite Account on Web/How to set up non NetSuite customer on web. How do we promote to each group. How does these transactions Affect NetSuite and will it run smoothly.
|  | in; retest after moving links |  |  |  | 1 | devise-based registration subsystem on Rails side
[6 empty] | 2 | test database of two clinics with clinicians
[6 empty] | 3 | run tests to see that clinician logging in from these clinics sees the correct prices, as does someone who is not looged in
[6 empty] | 4 | test that orders are being pushed to the Netsuite back-end with clinic-specific pricing
[6 empty] | 5 | confirm that correct descriptions, UPS 8.95 shipping charges, etc. are on the Netsuite-generated shopping cart
[6 empty] | 6 | confirm that clicking the checkout-option onl such a cart does the right thing:
[7 empty] | 1 | asks for CC information ( or do we have a bill-to-clinic at the end of the month option)
[7 empty] | 2 | confirms the CC through a payment gateway, and puts a provisional charge on the card
[7 empty] | 3 | isses the correct order to warehouse to have the products on the order pulled, packed, shipped
[7 empty] | 4 | sends the customer an email confirming that the order has been shipped and giving him a tracking number
[6 empty] | 7 | In R2: add option for administrator at a clinic to manage the set of clinicians registered through her clinic through the /admin subsysgtem on the Ruby-on-Rails middle-tier
[6 empty] | 8 | [ Look at My Account? — invoke the Netsuite function ]
[ What, specifically, do you want the user to be able to see/do? ]
[ Create a separate, aggregate account, for the clinic admin? ]

## Today
Sunday:
Finish up layout/ui goodies
| 1 | get dots into all product template pages
done |  |  | base_products/show.html.erb
done |  |  | product_sets/show.html.erb
done |  |  | product_types/show.thml.erb
done |  |  | product_types/_accessories.thml.erb
enough to test | 2 | modify web_descriptions for all base_products and product_sets in one top-level category to work with the dots
done | 3 | insert truck and latex free logos into all product templates
done |  | — | add tool tip explainations of what they mean if user hovers over them?
done | 4 | insert the logomark into views/layout/application.html.erb if want it on all pages; don't: not on home page; put it in all other page templates; candidate for partial in /views/shared
done |  | — | make the logomark clickable; it should return you to the site's home page.
| 5 | Working intermediate category links in breadcrumb trails?
done | 6 | close top-level category overlays which popup when user mouses over menu button when user leaves the menu — allowing, but not requiring him to close it by hitting the close button in the upper right
Monday:
Tie-off content Q&A when we have all of the images
| 1 | Insert product/category images that we are waiting on from Mandy
done:resized & in |  | — | got 3 specific images missing from existing categories
— move large PNGs for these images into the top-level category PNG image directories they belong in
|  | — | got a set of images for Quantum fitness equipment from Mandy
done |  |  | — make thumbnails and product page medium sized images for each of trhem
done |  |  | — insert original PNGs into directory for original images for Fitness category
— capture additions to all_large and all_small so can push them to Amazon S3. ( Or just repush everything? )
Tuesday: |  |  | — see how to handle the Quantum line: See note in catelog that says 'Have not modeled this'. | Add product-set semantics to coding of Quantum line of fitness equipment
Ok |  |  |  | — How are they coded in products_1229_...spreadsheet? as a set of base products. all in category: 68 Fitness/WeightEquitpment/'Universal'; change category name to 'Quantum'?
— The thing that is not modeled is the frame-color, specified with codes 740117-xxx (See pg 51 of the catelog) . Create an 'options' entry in base_products and product_sets?
done |  |  |  | — Consolidate base_products into product_sets where relevant; this will eliminate 1 of the 5 missing images
done |  |  |  |  | — Muscle Trainer
done |  |  |  |  | — Adjustable Cable Column
done |  |  |  |  | — Seated Leg Curl / Leg Extension
done |  |  |  |  | — Seated Abdominal/Back Extension
done |  |  |  |  | — Cable Crossover
done |  |  | — | fix long titles: MultiPress Bench/Incline/Shoulder Hip Abduction/Adduction
pullled from web |  | — | need 3 more images for Quantum line weight machines from Mandy:740046/47, 740059, 740062
| 2 | Insert product text on Compression Unit and Sleaves ( product no?) from Bill
| 3 | go through categories table; replace references to gray_3 with references to missing_image.jpg; create that image and put it in /images/categories; test codeto make sure it finds it rather than looking for missing_image-000.jpg.
| 4 | fix stretched category images as run across them
790110-000
Begin testing clinic-specific pricing/order submission
next | 1 | set up clinic and clinicians tables with test entries: 3 clinics
| 2 | confirm that one or two clinicians for each of these clinics can register/login and see the correct prices
| 3 | [ try putting some products in cart: follow header link to see cart; confirm that products are there, that descriptions are correct, that prices are correct ]
| 4 | [ try checkout link in header:
Does it invoke the Netsuite function properly?
Do all of the links from the Netsuite-generated pages work properly:
— those that go to other Netsuite-generated pages
— those (continue-shopping) that return the Rails-based middle tier

## 0410-0413
date added | date closed | status* | —>h?** | category |  |  | problem |  | key
[9 empty] | * | —>h? = pushed to heroku version of the site?
[9 empty] | ** | twfar='that way for a reason";
new since 04/10
UI/Layout related:
2012-04-12 | 2012-04-13 | done | yes |  |  | 1 | get rid of gray by going back to footer relative rather than fixed; retain code in directory tm3rorFF (for 'Fixed Footer') so can work on it later
2012-04-12 | 2012-04-13 | done:OK | yes |  |  | 2 | check it on iPhone also
Content-related
2012-04-10 | 2012-04-11 | done | yes |  |  | 1 | new image for pulls: category and individual product within that category
2012-04-10 | [5 empty] | 2 | Need correct Facebook link for application.html.erb
2012-04-10 | 2012-04-12 | done | yes |  |  | 3 | get in new products for iontopohoresis (6): 'products' table tuples, images, descriptions, pricing
[7 empty] | — | 710003-001 and 710003-000 violate the convention that we can strip the xxx ending off of image filenames and replace it with 000. I have dropped it; does it break other product pages in the site?
2012-04-10 | 2012-04-12 | done | no |  |  | 4 | get in new products for category 22:'products' table tuples, images, descriptions, pricing
2012-04-10 | 2012-04-13 | done | no |  |  | 5 | do the leaf-category swap in Bill's email of April 10th: ('Website comments): move Lifeline Fitness Cables from Resistive Exercise (#33) to Band & Tubing (#34)
2012-03-30 | 2012-04-13 | done | no |  |  | 6 | insert the two items that occur in two categories; Bill's email of March 30th: UI Issues I have noticed. Items 1 and 8: Sombra —> Clinic Supplies/Topical Analgesics; Sling (currently in Collars & Slings) ->Shoulder as well (so the category is not empty)
720296-xxx: actually, just recategorize from 30 to 42 (analygsics); retitle massage products'/lotions and gels' as 'massage lotions' as in print catalog
750164-000/xxx Slings; now in category 73 ; also to category 77 base_product 1737; now duplicated at 1742-46
[6 empty] | 7 | waiting compression and compression sleeves data from Bill; there were some images for these among those Mandy sent last -- but without tms part nos. Bill's email of April 9th
2012-04-13 | 2012-04-13 | done | no |  |  | 8 | eliminate intermediate categories in Lymthodema and Wound Care
2012-03-30 | 2012-04-13 | fixed | no |  |  | 9 | missing products in Wound Care/Scar Management?
2012-04-13 | 2012-04-13 | done | no |  |  | 10 | use digital TENS as category for Modalities/… Personal Electrotheraphy
2012-04-13 | 2012-04-13 | done | no |  |  | 11 | change text on placeholder image for missing category images from 'missing image' to 'no image'
| 2012-04-13 |  |  |  |  | 12 | go through entire site, reviewing thumbnails and large images
[7 empty] | — | Note: change in product.html.erb to use full image_filename rather than stripping it to 6 characters and pospending '-000' will cause some breakag; will have to rename some files in allLlarge and perhaps all_small to have -001, … endings
exanples of this 720331-001